## Feuille 2
Task | Sprint | Propriétaire | État | Starting Date | End Date | Duration | Description or/and notes
Created the Team Log-sheet | Sprint 1 | Zineb Bamouh | Done | 2025-01-24 | 2025-01-24 | 0:15 | none
Planned the tasks in the sprint planning sheet | Sprint 1 | everybody | Done | 2025-01-29 | 2025-01-29 | 1:00 | during a meeting we planned the us and tasks
Created the Sprint Planning sheet | Sprint 1 | Zineb Bamouh | Done | 2025-01-24 | 2025-01-24 | 0:01 | none
Description of US.1, US.2, US. 3, US. 4, US. 7, added in the issues | Sprint 1 | Zineb Bamouh | Done | 2025-01-31 | 2025-01-31 | 0:20 | none
Updated tasks for USs of sprint 1 | Sprint 1 | Ileass Bouhout | Done | 2025-01-31 | 2025-01-31 | 0:30 | none
Research on the technologies used | Sprint 1 | Ileass Bouhout | Done | 2025-01-24 | 2025-01-30 | 2:00 | Just the research part
Create the environment + set up db | Sprint 1 | Ileass Bouhout | Done | 2025-01-30 | 2025-01-31 | 3:00 | none
Created the repository | Sprint 1 | Ileass Bouhout | Done | 2025-01-31 | 2025-01-31 | 0:15 | none
Wrote the readme file | Sprint 1 | Ileass Bouhout | Done | 2025-01-31 | 2025-01-31 | 0:30 | none
Updated the readme file | Sprint 1 | Zineb Bamouh | Done | 2025-02-03 | 2025-03-03 | 0:30 | added technologies and environment commands
Worked on the Sign Up backend (US1) | Sprint 1 | Ileass Bouhout | Done | 2025-01-31 | 2025-02-03 | 2:00 | When sign up it goes to authentification
Worked on the Sign Up database (US1) | Sprint 1 | Ileass Bouhout | Done | 2025-02-03 |  |  | Instead of authen. we want the info goes to the DB info
Started Working on the Log in backend (US2) | Sprint 1 | Ileass Bouhout | Done | 2025-02-03 | 2025-02-03 | 0:45 | Only the begginning
Took over and worked on the Log in Backend (US2) | Sprint 1 | Julian Valencia | Done | 2025-02-03 | 2025-02-03 | 0:30 | Started to work on Logging In
Worked on Log in Backend (US2), Django2 Database | Sprint 1 | Julian Valencia | Done | 2025-02-03 | 2025-02-03 | 1:00 | Could not recognise the username in DB
Worked on Log in Backend (US2), FTC_Chat Database | Sprint 1 | Julian Valencia | Done | 2025-02-03 | 2025-02-03 | 2:00 | Logging in works, directs to home when authenticated (for now)
Started and Finalized frontend and UI registration page | Sprint 1 | Zineb Bamouh | Done | 2025-02-04 | 2025-02-04 | 2:00 | I might want to change the color scheme because the purple looks too much like slack
Handled Errors when Logging In (US2) | Sprint 1 | Julian Valencia | Done | 2025-02-04 | 2025-02-04 | 1:00 | Logging in now displays a success message, as well as an error message when it fails
Worked on dashboard frontend | Sprint 1 | Zineb Bamouh | In Progress | 2025-02-05 | 2025-02-05 | 5:00 | sidebar and channels done, but not the rest
Worked on homepage frontend | Sprint 1 | Ileass Bouhout | Done | 2025-02-06 | 2025-02-06 | 2:00 | Added navigation bar and "register" and "login" buttons
Worked on the Log In page | Sprint 1 | maghnisafouane@gmail.com | Done | 2025-02-03 | 2025-02-04 | 2:00 | Created a fully functional and aesthetic Log In page.
Research on HTML/CSS | Sprint 1 | maghnisafouane@gmail.com | Done | 2025-01-24 | 2025-01-24 | 1:30 | Discovering how to create a page in HTML/CSS.
Creating a draft Log In page | Sprint 1 | maghnisafouane@gmail.com | Done | 2025-01-27 | 2025-01-27 | 1:30 | Created a log in page not focusing on any aesthetic.