## Feuille 1
Issue # | US #: Task Title | Sprint | Person Name | User Story Points | Priority | Risk | Due date | Description
10 | US 1-2: Design a user-friendly interface for signing in and logging in | Sprint 1 | Zineb & Safouane | 5 | High | High | 2025-02-06 | User-friendly design for the register and login page Must design a home page where buttons for log in and register can be found Boutons are routed to appropriate pages with the right forms High risk: without it, the user can't access the dashboard therefore can't use the application Story point of 5 (the maximum): need it to get the user information to be sent the database
11 | US 1-2: Implementing a database for the registered account | Sprint 1 | Ileass & Julian | 5 | High | High | 2025-02-06 | Interactive and real-time update of the database When the user submit the registration form, the information are sent into the database (if there's already an email linked to an account, he won'T be able to create an account. When the user submit the login form, the information are retrieve from database to verify its credentials (if not the right one, he can't connect) High risk: without it we can't retrieve user information to use them (e.g. knowing if he's admin or member will link to the right dashboard with the righ functionalities) Story point of 5 (the maximum): need it to have access to the user information
13 | US 7: Implementing a design a user-friendly interface for the dashboard | Sprint 1 | Zineb | 4 | Medium | Medium | 2025-02-12 | Have a dashboard for both admin and member. However, when a member is logged in, he doesn't have access to the admin functionalities When the member is authentified, there should be a function where all the admin functionalities disapears (e.g. the boutons that let you create and delete would disapear from the dashboard which is implemented in another US) Nice UI and UX design for convinience and aesthetic Medium risk: having a nice UI doesn't affect the functionalities that would be created in other USs, however it should be done ASAP to know where to put the boutons so that when we implement the functionalities of removing the button when a member is authentified, it doesn't impact the rest of the dashboard Story point of 4: the same reason as stated above, but UI won't slow down the implementation of other USs
14 | US 3: Implementing a database to keep track of all teams per admin | Sprint 1 | Ileass | 5 | High | High | 2025-02-12 | Interactive and real-time update of the database When a specific user is logged in, only they own teams shows up on their dashboard (Admin can view theirs teams they created and members can view only teams ig they access to the channel inside that team Information are retrieve from the db to show up on the dashboard High risk: without it we can't keep the team's information and they would disapear everytime the admin log out Story point of 5 (the maximum): the same reason as stated above
15 | US 3: Design a user-friendly interface for admin to view all teams | Sprint 1 | Sarvesh | 4 | Medium | Medium | 2025-02-14 | Have a pop up page appearing when the admin press on the button create a new team. It's more convenient, if it's a pop up then redirecting to a new page. A form should appear asking for the name team and the information should be sent in the database When admin press a button to finish the process, the new team should appear in his dashboard If admin have multiple teams he should be able to switch between them